## Fig 13
Figure 13: Example of a Hybrid Network (Planning) Diagram (for a Training Project)
| WEEK 1 |  | WEEK 2 |  | WEEK 3 |  | WEEK 4 |  | WEEK 5 |  | WEEK 6
UNIT | [8 empty] | Learn, and develop skills
PERSONNEL |  | Meet |  |  |  | Meet to-
|  | together |  |  |  | gether to
|  | to assess |  |  |  | schedule
|  | person- |  |  |  | workload
|  | nel's job |  |  |  | during
UNIT | Meet to- | knowledge |  |  |  | training
MANAGER | gether to | & skills |  |  | Meet | program
| analyze |  | Meet to-
| unit jobs |  | gether to |  | together
| and iden- |  | identify
| tify knowl- |  | training |  | to
PERSONNEL | edge and | Test | needs
DEPT. | skill re- | unit per- |  |  | schedule
| quirements | sonnel's
|  | measura- |  |  | training
|  | ble skills |  | Identify /
|  |  |  | select | sessions
TRAINING |  |  |  | training |  | Schedule | Prepare/train |  |  | Conduct
DEPT. |  |  |  | materials |  | trainers | trainers |  |  | training program
and their
sources
PURCHASING
DEPT. |  |  |  | Order |  | Receive
|  |  |  | training |  | training
|  |  |  | materials |  | materials
|  |  | Activity |  | Input to subsequent activity |  |  | Lag (Wait) Time
Copyright © 1989,1995, 2012 by R. D. Cecil & Co.

## Fig 12
Figure 12: Simplified PERT Network for Building a Military Aircraft30
102.1
Engine |  | 2 | [6 empty] | 9 |  | CRITICAL
PATH
17.3
| 17.3 |  |  |  |  | 56.0 |  |  |  | 10.0
Fuselage |  |  |  |  | 4 |  | 8
12.3
|  |  |  | 10.3 |  |  | 40.0 |  | 8.0
Wings | 1 |  | 3 |  |  | 7 |  | 10 |  |  | 13
12.0
40.6
Tail |  | 8.6 |  |  | 6 |  |  |  | 11
52.0
GFAE |  |  | 5 | [6 empty] | 12
1. Program Go-Ahead | [6 empty] | 7. Award Wings Subcontract
2. Initiate Engine Procurement | [6 empty] | 8. Complete Manufacture of Fuselage
3. Complete Plans/Specifications | [6 empty] | 9. Complete Assembly of Fuselage/Engine
4. Complete Fuselage Drawings | [6 empty] | 10. Receive Wings from Subcontractor
5. Submit GFAE (Government Furnished | [6 empty] | 11. Receive Tail from Subcontractor
Aircraft Equipment -- | [6 empty] | 12. Receive GFAE
e.g., electronic gear) | [6 empty] | 13. Complete Aircraft
6. Award Tail Assembly Subcontract
a = most optimistic time (least time) required for an activity
m = most likely or realistic time required
b = pessimistic (most) time required (considering adverse contingencies)
Te = Estimated Time Required = a + 4m + b
6
T1 = Actual Time Taken
Ta = Slack Time = T1 - Te

## Fig 11
Figure 11: Gantt-Like Project Schedule with Milestones
(Adapted version of a product development schedule for a personal copy machine)29
| DWG | FAB | ASSY | TEST
Bench
(3 units) |  |  |  |  | MOD
|  | DWG |  |  | SOFT |  |  | DVT
Engineering | [10 empty] | RCP
(13 units) |  |  | DWG |  | FAB | ASSY |  | DEBUG QAT
[7 empty] | DWG |  | FAB | ASSY
Prototype
(19 units) | [10 empty] | DVT
REG
DWG
Production
[10 empty] | PROD |  | INS | SIM | DEBUG
|  |  | Time | [9 empty] | QAT
DVT
DWG: Design/Drawing MOD: Modification DEBUG: Debugging PROD: Production
FAB: Fabrication SOFT: Software devel't QAT: Quality Assur.Test INS: Inspection
ASSY: Assembly DVT: Design Verif'n Test REG: Pass Gov't Regs SIM: Simulate Mass
TEST: Testing RCP: Reliability of Regulations Production
Critical Parts

## Fig 10
Figure 10: Simplified Gantt (Bar) Chart for the Construction of a House27
Lay Foundation
Erect Frame
Install Siding
Finish Exterior
Install Plumbing
Install Wiring
Install Millwork
Plaster Walls
Finish Interior
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Elapsed Time (in Weeks)