## Sheet1
Copyright © 2007, 2012 by R.D. Cecil & Co.
Comparison of OC, OD, and MD/OD Projects
| CONSULTING FIRM |  | CONSULTANT-LED |  | CONSULTANT + TRAINERs + FACILITATORs
| CHANGE MANAGEMENT PROJECT |  | OD INTERVENTION |  | INTEGRATED MD/OD PROJECT
| Usually done by large organizations. |  | Often done by mid-size and smaller organizations. |  | Can be conducted by almost any organization.
| Looking for identified and unidentified prob- |  | Usually aimed at solving perceived problems, |  | Can involve factor analyses of most if not all | organizational structure and systems --
| lems; also looking for opportunities to |  | where the suspected causes are (a) personnel's |  | aspects of operations, but generally focuses | and personnel's motivation, attitudes, interac-
| improve all aspects of operations by analyz- |  | motivation, attitudes, skills, interactions, behavior, |  | participants' attention on the "people aspects." | tions, behavior, managerial/leadership styles,
| ing many operating variables, systems and |  | managerial/leadership styles, and performance, |  | May be preceded by analysis of, and goal-set- | and performance -- are suspected causes.
| processes in great breadth and depth. |  | and (b) the organization's structure, processes, and |  | ting and planning concerning, the organization's
|  |  | systems. |  | major units or functional areas.
| Consultants, considered the experts, use |  | Uses "Action Research" approach, where the |  | Consultant/instructor(s)/facilitator(s) guide partic-
| the Analytic Approach to identify problems |  | Analytic Approach process is facilitated by the |  | ipants' use of the Analytic Approach as they
| and formulate and recommend solutions. |  | consultant, but personnel are considered the ex- |  | apply what they have been learning to better
|  |  | perts and are guided in their analysis of the situa- |  | analyze situations and formulate, choose, and
|  |  | tion, formulation of solutions, and decision-making. |  | implement improvements (including solutions).
1. | Recognition that organization has problems. | 1. | Recognition that organization has problem(s). | 1. | Awareness that organization has recognized
problems, unrecognized problems, and also
opportunities to improve many other aspects
of operations.
2. | Hire consulting firm. | 2. | Hire "change" or "positive change" consultant. | 2. | Hire/assign consultant and trainer(s)/facilitator(s).
3. | Consultants research organization. | 3. | Consultant researches organization. | 3. | Consultant researches organization.
PHASE 1 (PREPARATION) - Step 1
(see Figures 1.2 and 11.1)
4. | Consultants and managers orient person- | 4. | Consultant and managers orient personnel | 4. | Consultant and managers orient personnel
| nel regarding project to be conducted. |  | regarding project to be conducted. |  | regarding project to be conducted.
5. | Consultants collect information: | 5. | Consultant collects information: | 5. | Consultant collects information:
| a. conduct interviews; |  | a. conducts interviews; |  | a. conducts interviews;
| b. conduct attitude surveys; and |  | b. conducts attitude surveys; and |  | b. conducts attitude surveys; and
| c. collect market, production, R&D, finan- |  | c. familiarizes self with organization's market, |  | c. familiarizes self with organization's market,
| cial, systems, HR and other data/info. |  | product/service, financial and other data/info. |  | product/service, financial & other data/info.
PHASE 1 - Steps 2a - 2c
(see Figures 1.2 and 11.1)
Superiors meet with subordinates to discuss
project and formulate (operating and) develop-
mental objectives.
Copyright © 2007, 2012 by R. D. Cecil and Company
TRAINING / APPLICATION PROGRAM
(see Figure 1.2; also PHASE 2 in Figure 11.1)
|  |  |  | 6a. | Conduct training portions of Program Modules.
| Process Overview (Emphasis on Problem- |  | Process Overview (Emphasis on Problem- |  | Process Overview (Emphasis on Improving
| Solving): Consultants . . . |  | Solving): Consultant guides personnel's |  | Many Aspects of Operations): Consultant facilitates
| (1) Analyze Problems; (2) Identify Causes; |  | (1) Analysis of Problem(s); (2) Identification of |  | (1) Analyzing key influential factors; (2) Determin-
| (3) Formulate Solutions; (4) Recommend |  | Possible Causes; (3) Formulation of Alternative |  | ing Functionality/Dysfunctionality for Unit/Organi-
| Solutions |  | Solutions; (4) Choice of Solutions |  | zation; (3) Formulating Plans for Improving Key Fac-
tors (Aspects of Operations); (4) Choosing Plans
6. | Consultants analyze information on all | 6. | Consultant initially analyzes information (to gain | 6b. | During the facilitated Superior-Subordinates
| aspects of operations. |  | insights that will help extract analyses and solu- |  | Discussion Sessions that follow training sessions,
|  |  | tions from personnel), and then guides personnel's |  | participants apply the Analytic Approach as they
|  |  | analysis of situation(s). |  | use what they have learned (and any additional
information collected/provided) to analyze situa-
tions (and then formulate and choose changes,
improvements, or solutions).
7. | Consultants feed back information. | 7. | Consultant feeds back information to stakeholders. |  | Participants agree on analyses of situations, on
8. | Consultant gets agreement on problem(s) | 8. | Consultant gets agreement on analysis of situa- |  | recognized problems and their causes, and on
| identified. |  | tions and the problems (and causes) identified. |  | opportunities to improve other factors that affect
their development, activities, and performance.
9. | Consultants solicit inputs that will help them | 9. | Consultant solicits ideas for solving problems. | 6c. | Participants formulate possible solutions and
| formulate solutions. |  |  |  | improvements (which include Action Plans for
their implementation).
10. | Consultants formulate and feed back solu- | 10. | Consultant feeds back solutions (which often
| tions (which may involve a training program). |  | involve a training and development program).
11. | Consulting firm gets agreement on solutions. | 11. | Consultant gets agreement on solutions. | 6d. | Participants choose improvements and solu-
tions (including Action Plans for implementation).
12. | Consultants collect info about possible Action | 12. | Consultant collects information about possible
| Plans for implementing solution(s). |  | Action Plans for implementing solution(s).
13. | Consultants formulate and feed back | 13. | Consultant feeds back Action Plans.
Action Plans.
14. | Consultant gets agreement on Action Plan(s). | 14. | Consultant gets agreement on Action Plan(s).
15. | Organization implements Action Plan(s) | 15. | Organization implements Action Plan(s) | 7. | Units and organization implement solutions
| (which may involve training and development). |  | (which often involve training and development). |  | and improvements (using Action Plans).
16. | Consultant and organization evaluate results. | 16. | Consultant and organization evaluate results. | 8. | Consultant and organization evaluate results.
17. | Consultant and organization ensure accept- | 17. | Consultant and organization ensure acceptance | 9. | Consultant and organization ensure accept-
| ance of change effort. |  | of change effort. |  | ance of change effort.
18. | Consultants depart. | 18. | Consultant departs. | 10. | Consultant (and any others) depart(s).