## Fig 11
Figure 7: Gantt-Like Project Schedule with Milestones
(Adapted version of a product development schedule for a personal copy machine)29
| DWG | FAB | ASSY | TEST
Bench
(3 units) |  |  |  |  | MOD
|  | DWG |  |  | SOFT |  |  | DVT
Engineering | [10 empty] | RCP
(13 units) |  |  | DWG |  | FAB | ASSY |  | DEBUG QAT
[7 empty] | DWG |  | FAB | ASSY
Prototype
(19 units) | [10 empty] | DVT
REG
DWG
Production
[10 empty] | PROD |  | INS | SIM | DEBUG
|  |  | Time | [9 empty] | QAT
DVT
DWG: Design/Drawing MOD: Modification DEBUG: Debugging PROD: Production
FAB: Fabrication SOFT: Software devel't QAT: Quality Assur.Test INS: Inspection
ASSY: Assembly DVT: Design Verif'n Test REG: Pass Gov't Regs SIM: Simulate Mass
TEST: Testing RCP: Reliability of Regulations Production
Critical Parts