## Fig_4.4_Pert
Figure 4.5: Simplified PERT Network for Building a Seagoing Luxury Yacht | [12 empty] | Page 94
(times shown in weeks; time lines not drawn to scale; some lines include "dead"/waiting time)
28.0
Engine |  |  | 3 |  |  |  |  | 9
1.0
|  | 2.0 |  |  | 15.0 |  |  |  |  | 2.0
Hull and |  |  |  | 5 |  |  | 8
engine spaces
3.0
Super- |  |  |  | 8.0 |  | 15.0 |  |  | 3.0
structure | 1 | 2 |  |  | 6 |  |  | 10 |  |  | 13
4.0
4.0
|  |  |  | 12.0 |  |  | 20.0
Interior spaces |  | 2.0 |  |  |  | 7 |  |  | 11
3.0
30.0
Electronic gear |  |  | 4 | [6 empty] | 12 |  | CRITICAL
[6 empty] | 28 30 32 | [5 empty] | PATH
[6 empty] | (a) (m) (b) | [5 empty] | 40.0 weeks
1. Start project
2. Complete plans & specifications | [6 empty] | 8. Hull completed; complete engine space
3. Order custom engines/controls package | [6 empty] | 9. Install engines
4. Order custom electronic equipment | [6 empty] | 10. Complete superstructure
5. Begin hull construction | [6 empty] | 11. Complete interior spaces/appointments
6. Begin superstructure construction | [6 empty] | 12. Install engine controls & electronic gear
7. Begin interior spaces construction | [6 empty] | 13. Yacht completed
a = most optimistic time (least time) required for an activity
m = most likely or realistic time required
b = pessimistic (most) time required (considering adverse contingencies)
Estimated time required = a + 4m + b
6